## Project Parameters
The Company Name
Project Parameters
Company Confidential
2004-12-12
Gray cells will be calculated for you. You do not need to enter anything in them.
Project type | Account manager | Project manager | Business analyst | Process specialist | Finance specialist | Administrative staff | Total
Business continuity planning | 15% | 20% | 30% | 10% | 15% | 10% | 100%
Business process re-engineering | 10% | 10% | 10% | 50% | 10% | 10% | 100%
Cost reduction | 10% | 20% | 14% | 20% | 240% | 10% | 314%
Process improvement | 10% | 20% | 10% | 40% | 10% | 10% | 100%
Sarbanes-Oxley | 10% | 20% | 20% | 20% | 20% | 10% | 100%
Strategic planning | 10% | 10% | 50% | 0% | 20% | 10% | 100%
Blended rates | 2500 | 2250 | 200 | 175 | 150 | 50

## Project Planning
The Company Name
Project Planning
Company Confidential
Gray cells will be calculated for you. You do not need to enter anything in them.
Project name | Project type | Estimated start | Estimated finish | Estimated work (hours) | Duration (days)
A. Datum Corporation | Business continuity planning | 2005-01-04 | 2005-03-04 | 200 | 60
Adventure Works | Business process re-engineering | 2005-01-20 | 2005-02-21 | 400 | 31
Alpine Ski House | Cost reduction | 2005-02-06 | 2005-04-16 | 500 | 70
Baldwin Museum of Science | Process improvement | 2005-02-24 | 2005-04-25 | 150 | 61
Blue Yonder Airlines | Cost reduction | 2005-03-08 | 2005-03-18 | 250 | 10
City Power & Light | Sarbanes-Oxley | 2005-03-19 | 2005-04-29 | 300 | 40
Coho Vineyard | Strategic planning | 2005-04-10 | 2005-04-20 | 500 | 10
Coho Vineyard & Winery | Sarbanes-Oxley | 2005-05-12 | 2005-06-22 | 450 | 40
Coho Winery | Cost reduction | 2005-04-18 | 2005-05-12 | 750 | 24
Consolidated Messenger | Process improvement | 2005-06-30 | 2005-08-30 | 180 | 60
Contoso, Ltd. | Cost reduction | 2005-05-23 | 2005-07-21 | 250 | 58
Contoso Pharmaceuticals | Business process re-engineering | 2005-06-14 | 2005-08-12 | 200 | 58
Fabrikam, Inc. | Cost reduction | 2005-01-16 | 2005-08-15 | 250 | 209
Fourth Coffee | Sarbanes-Oxley | 2005-07-17 | 2005-09-01 | 240 | 44
Graphic Design Institute | Sarbanes-Oxley | 2005-07-25 | 2005-09-30 | 320 | 65
Humongous Insurance | Cost reduction | 2005-08-01 | 2005-10-01 | 550 | 60
Litware, Inc. | Strategic planning | 2005-08-20 | 2005-10-02 | 350 | 42
Lucerne Publishing | Business continuity planning | 2005-09-02 | 2005-11-12 | 200 | 70
Margie's Travel | Cost reduction | 2005-09-12 | 2005-11-25 | 220 | 73
Northwind Traders | Process improvement | 2005-10-12 | 2005-12-20 | 600 | 68
Proseware, Inc. | Sarbanes-Oxley | 2005-10-24 | 2005-12-14 | 525 | 50
School of Fine Art | Cost reduction | 2005-11-04 | 2005-11-24 | 180 | 20
TOTAL HOURS |  |  |  | 7565

## Project Tracking
The Company Name
Project Tracking
Company Confidential
Gray cells will be calculated for you. You do not need to enter anything in them.
Project name | Actual start | Actual finish | Actual work (hours) | Actual duration (days)
A. Datum Corporation | 2005-01-04 | 2005-03-09 | 220 | 65
Adventure Works | 2005-01-25 | 2005-02-28 | 390 | 33
Alpine Ski House | 2005-02-10 | 2005-04-23 | 500 | 73
Baldwin Museum of Science | 2005-02-22 | 2005-04-29 | 145 | 67
Blue Yonder Airlines | 2005-03-09 | 2005-03-28 | 255 | 19
City Power & Light | 2005-03-19 | 2005-05-05 | 310 | 46
Coho Vineyard | 2005-04-12 | 2005-04-27 | 510 | 15
Coho Vineyard & Winery | 2005-04-17 | 2005-05-16 | 790 | 29
Coho Winery | 2005-05-15 | 2005-06-24 | 430 | 39
Consolidated Messenger | 2005-05-24 | 2005-07-24 | 235 | 60
Contoso, Ltd. | 2005-06-16 | 2005-08-16 | 235 | 60
Contoso Pharmaceuticals | 2005-07-02 | 2005-09-25 | 190 | 83
Fabrikam, Inc. | 2005-01-18 | 2005-08-16 | 230 | 208
Fourth Coffee | 2005-07-19 | 2005-09-15 | 225 | 56
Graphic Design Institute | 2005-07-26 | 2005-10-20 | 305 | 84
Humongous Insurance | 2005-08-01 | 2005-10-14 | 565 | 73
Litware, Inc. | 2005-08-28 | 2005-10-21 | 350 | 53
Lucerne Publishing | 2005-09-04 | 2005-11-15 | 205 | 71
Margie's Travel | 2005-09-13 | 2005-11-29 | 230 | 76
Northwind Traders | 2005-10-22 | 2005-12-24 | 560 | 62
Proseware, Inc. | 2005-10-14 | 2005-12-10 | 540 | 56
School of Fine Art | 2005-11-04 | 2005-11-20 | 190 | 16
TOTAL HOURS |  |  | 7610

## Planned Project Totals
The Company Name
Planned Project Totals
Company Confidential
Gray cells will be calculated for you. You do not need to enter anything in them.
Project name | Account manager | Project manager | Business analyst | Process specialist | Finance specialist | Administrative staff | Total
A. Datum Corporation | 75000 | 90000 | 12000 | 3500 | 4500 | 1000 | 186000
Adventure Works | 100000 | 90000 | 8000 | 35000 | 6000 | 2000 | 241000
Alpine Ski House | 125000 | 225000 | 14000 | 17500 | 180000 | 2500 | 564000
Baldwin Museum of Science | 37500 | 67500 | 3000 | 10500 | 2250 | 750 | 121500
Blue Yonder Airlines | 62500 | 112500 | 7000 | 8750 | 90000 | 1250 | 282000
City Power & Light | 75000 | 135000 | 12000 | 10500 | 9000 | 1500 | 243000
Coho Vineyard | 125000 | 112500 | 50000 | 0 | 15000 | 2500 | 305000
Coho Vineyard & Winery | 112500 | 202500 | 18000 | 15750 | 13500 | 2250 | 364500
Coho Winery | 187500 | 337500 | 21000 | 26250 | 270000 | 3750 | 846000
Consolidated Messenger | 45000 | 81000 | 3600 | 12600 | 2700 | 900 | 145800
Contoso, Ltd. | 62500 | 112500 | 7000 | 8750 | 90000 | 1250 | 282000
Contoso Pharmaceuticals | 50000 | 45000 | 4000 | 17500 | 3000 | 1000 | 120500
Fabrikam, Inc. | 62500 | 112500 | 7000 | 8750 | 90000 | 1250 | 282000
Fourth Coffee | 60000 | 108000 | 9600 | 8400 | 7200 | 1200 | 194400
Graphic Design Institute | 80000 | 144000 | 12800 | 11200 | 9600 | 1600 | 259200
Humongous Insurance | 137500 | 247500 | 15400 | 19250 | 198000 | 2750 | 620400
Litware, Inc. | 87500 | 78750 | 35000 | 0 | 10500 | 1750 | 213500
Lucerne Publishing | 75000 | 90000 | 12000 | 3500 | 4500 | 1000 | 186000
Margie's Travel | 55000 | 99000 | 6160 | 7700 | 79200 | 1100 | 248160
Northwind Traders | 150000 | 270000 | 12000 | 42000 | 9000 | 3000 | 486000
Proseware, Inc. | 131250 | 236250 | 21000 | 18375 | 15750 | 2625 | 425250
School of Fine Art | 45000 | 81000 | 5040 | 6300 | 64800 | 900 | 203040
TOTAL Cost | 1941250 | 3078000 | 295600 | 292075 | 1174500 | 37825 | 6819250
TOTAL Hours | 776.5 | 1368 | 1478 | 1669 | 7830 | 756.5 | 13878

## Actual Project Totals
The Company Name
Actual Project Totals
Company Confidential
Gray cells will be calculated for you. You do not need to enter anything in them.
Project name | Account manager | Project manager | Business analyst | Process specialist | Finance specialist | Administrative staff | Total
A. Datum Corporation | 82500 | 99000 | 13200 | 3850 | 4950 | 1100 | 204600
Adventure Works | 97500 | 87750 | 7800 | 34125 | 5850 | 1950 | 234975
Alpine Ski House | 125000 | 225000 | 14000 | 17500 | 180000 | 2500 | 564000
Baldwin Museum of Science | 36250 | 65250 | 2900 | 10150 | 2175 | 725 | 117450
Blue Yonder Airlines | 63750 | 114750 | 7140 | 8925 | 91800 | 1275 | 287640
City Power & Light | 77500 | 139500 | 12400 | 10850 | 9300 | 1550 | 251100
Coho Vineyard | 127500 | 114750 | 51000 | 0 | 15300 | 2550 | 311100
Coho Vineyard & Winery | 197500 | 355500 | 31600 | 27650 | 23700 | 3950 | 639900
Coho Winery | 107500 | 193500 | 12040 | 15050 | 154800 | 2150 | 485040
Consolidated Messenger | 58750 | 105750 | 4700 | 16450 | 3525 | 1175 | 190350
Contoso, Ltd. | 58750 | 105750 | 6580 | 8225 | 84600 | 1175 | 265080
Contoso Pharmaceuticals | 47500 | 42750 | 3800 | 16625 | 2850 | 950 | 114475
Fabrikam, Inc. | 57500 | 103500 | 6440 | 8050 | 82800 | 1150 | 259440
Fourth Coffee | 56250 | 101250 | 9000 | 7875 | 6750 | 1125 | 182250
Graphic Design Institute | 76250 | 137250 | 12200 | 10675 | 9150 | 1525 | 247050
Humongous Insurance | 141250 | 254250 | 15820 | 19775 | 203400 | 2825 | 637320
Litware, Inc. | 87500 | 78750 | 35000 | 0 | 10500 | 1750 | 213500
Lucerne Publishing | 76875 | 92250 | 12300 | 3587.5 | 4612.5 | 1025 | 190650
Margie's Travel | 57500 | 103500 | 6440 | 8050 | 82800 | 1150 | 259440
Northwind Traders | 140000 | 252000 | 11200 | 39200 | 8400 | 2800 | 453600
Proseware, Inc. | 135000 | 243000 | 21600 | 18900 | 16200 | 2700 | 437400
School of Fine Art | 47500 | 85500 | 5320 | 6650 | 68400 | 950 | 214320
TOTAL Cost | 1955625 | 3100500 | 302480 | 292162.5 | 1071862.5 | 38050 | 6760680
TOTAL Hours | 782.25 | 1378 | 1512.4 | 1669.5 | 7145.75 | 761 | 13248.9